## Sheet1
Cost Estimate
| Project Name: Cober Insights |  | Date: | 2019-12-01
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
WBS # | WBS Categories |  | Labor (#hours) | $/hr | $ Total | Labor | $ Total | Labor $ | Non-labor $ | Total Cost
1 | Phase 1 - Initiating (Concept)
1.1 | Develop Project Charter | TKN | 25 | 65 | 1625 |  | 0 | 1625 |  | 1625
1.2 | Identify Stakeholders | TKN | 25 | 65 | 1625 |  | 0 | 1625 |  | 1625
1.3 | Initiate project documentation | TKN | 25 | 65 | 1625 |  | 0 | 1625 |  | 1625
2 | Phase 2 - Planning
2.1 | Team planning meeting | TKN | 3 | 65 | 195 |  | 0 | 195 |  | 195
2.1.1 | Define sprint schedule | TKN | 3 | 65 | 195 |  | 0 | 195 |  | 195
2.2 | Scope Management | TKN | 3 | 65 | 195 |  | 0 | 195 |  | 195
2.2.1 | Prepare and define scope | TKN | 3 | 65 | 195 |  | 0 | 195 |  | 195
2.3 | Human Resource Management | TKN, HR/MK | 4 | 85 | 340 |  | 0 | 340 |  | 340
2.3.1 | Identify one System Administrator from current IT staff | HR | 1 | 94 | 94 |  | 0 | 94 |  | 94
2.3.2 | Hire one additional Computer Engineer | HR | 4 | 94 | 376 |  | 0 | 376 |  | 376
2.3.3 | Hire one Manufacturing Data Scientist | HR | 4 | 94 | 376 |  | 0 | 376 |  | 376
2.3.4 | Hire one Software Engineer | HR | 4 | 94 | 376 |  | 0 | 376 |  | 376
2.3.5 | Hire one Software Developer | HR | 4 | 94 | [5 empty] | 0
2.3.6 | Hire one UX/UI Designer | HR | 4 | 94 | 376 |  | 0 | 376 |  | 376
2.3.7 | Hire one Info Security Specialist | HR | 4 | 94 | 376 |  | 0 | 376 |  | 376
2.3.8 | Schedule First Townhall to introduce project team members | TKN | 1 | 65 | 65 |  | 0 | 65 |  | 65
2.4 | Collect requirements | TKN | 40 | 65 | 2600 |  | 0 | 2600 |  | 2600
2.4.1 | Estimate activities requirements (non-labour) | TKN | 40 | 65 | 2600 |  | 0 | 2600 |  | 2600
2.4.2 | Prepare requirement change request process | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.5 | Schedule Management | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.5.1 | Review individual resource schedules (ie. vacations, known busy periods...) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.5.2 | Define activities | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.5.2.1 | Sequence activities | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.5.3 | Identify activities dependencies | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.5.4 | Estimate activities resources (labour) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.5.5 | Estimate activities duration | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.5.5.1 | Prepare and define schedule | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.6 | Prepare estimate of cost baseline | TKN, MK | 4 | 85 | 340 |  | 0 | 340 |  | 340
2.6.1 | Estimate activities cost (labour and non-labour) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.7 | Risk Management | TKN, MK
2.7.1 | Prepare risk management questionnaire for brainstorming session | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.7.2 | Identify risk | TKN | 16 | 65 | 1040 |  | 0 | 1040 |  | 1040
2.7.2.1 | Define risk appetite & intolerance | TKN, MK | 2 | 85 | 170 |  | 0 | 170 |  | 170
2.7.3 | Perform qualitative risk analysis | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.7.4 | Perform quantitative risk analysis | TKN, MK | 4 | 85 | 340 |  | 0 | 340 |  | 340
2.7.5 | Document response plan | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520
2.7.6 | Identify possible fallback plan | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520
2.8 | Procurement Management | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520
2.8.1 | Plan & Conduct third party analysis for external resources (eWon Flexy alternative) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.8.1.1 | Control procurement (manage contract) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.8.1.2 | Close procurement (ensure proper execution of contract) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.8.2 | Plan & Conduct third party analysis for external resources (Azure) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.8.2.1 | Control procurement (manage contract) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.8.2.2 | Close procurement (ensure proper execution of contract) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.9 | Milestone Mapping | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
2.9.1 | Survey project team for possible milestone identifiers | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
3 | Phase 3 - Executing (Designing, Implementation (& build), Testing)
3.1 | Phase 1 - Architecture
3.1.1 | Meeting to discuss stakeholder needs and concerns with architecture (ie. security, reporting templates...) | TKN, StkHld | 16 | 65 | 1040 |  | 0 | 1040 |  | 1040
3.1.1.1 | Meeting to discuss high level connections | IS, IT | 8 | 94 | 752 |  | 0 | 752 |  | 752
3.1.2 | SPRINT 1.1 Cloud Architecture | IS, IT
3.1.2.1 | Define single connectivity between eWon Flexy and Azure Iot Hub MQTT | IT, CE | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.1.2.2 | Define multiple connectivity between eWon Flexy and Azure Iot Hub MQTT (as Cober has multiple clients with multiple machines...) | IT, CE | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.1.2.3 | Test message relay between eWon Flexy and Azure Iot Hub MQTT | IT | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.1.2.4 | Define security protocols for multi connectivity to ensure client data confidentiality | IS, IT | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.1.2.5 | SPRINT 1.2 Data to Cloud Mapping | IS, IT, DS
3.1.2.6 | Map data parsing channels from Azure IoT Hub to Azure Service Bus | IS, IT, DS | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.2.7 | Map data parsing channels from Azure IoT Hub to Stream Anayltics Job | IS, IT, DS | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.2.8 | Map data parsing channels from Azure IoT Hub to Blob Storage | IS, IT, DS | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.2.9 | SPRINT 1.3 Cloud to App Connection | IS, IT, CE
3.1.2.10 | Define Azure Service Bus connection to Logic Apps & Email functions | IS, IT, CE | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.2.11 | Define Stream Analytics Jobs to Power BI's Live Dashboards | IS, IT, CE | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.2.12 | Define Power BI's Live Dashboards connectivity with Blob Storage and SQL/App Service | IS, IT, CE | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.3 | SPRINT 1.4 SQL DB Architecture | DBA
3.1.3.1 | Review E-R Model, SQL DB and Job Scheduler | DBA, CE | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.3.2 | Configure SQL DB with Cober Data Analytics Flask Webapp | DBA, CE | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.3.3 | Configure basic SQL reports based on internal expertise input (ie. what would machine tech's want to see) | DBA, CE | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.3.4 | SPRINT 1.5 Security Assignment | IS, IT, DBA
3.1.3.5 | Assign personel to cloud security | IS, IT | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.1.3.6 | Assign personel as DBMA | IS, IT | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.1.3.7 | Define security change management protocol | IS, IT, DBA | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.1.3.8 | SPRINT 1.6 Perform security testing | IS, IT, DBA, CE, PT
3.1.4 | SPRINT 1.7 App Access Right Config | IT, SD, SE, UX
3.1.4.1 | Determine population for the following security access levels Global Administrator, Company Administrator, Regular User | IT, SD, UX | 25 | 94 | 2350 |  | 0 | 2350 |  | 2350
3.1.4.2 | Determine security access level rights (add, remove users, restrict views, export functionality) | IS, IT | 25 | 94 | 2350 |  | 0 | 2350 |  | 2350
3.1.4.3 | SPRINT 1.8 Data to Application config | CE, DS, SE, SD
3.1.4.4 | Identification of data tags (service bus, blob storage, Power BI Rest API) | DS | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.4.5 | Perform data tag formatting testing to identify breaks | CE, DS, SE, SD | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.5 | SPRINT 1.9 App User Interface Configuration- Functional Specifications & Testing | SD, UX
3.1.5.1 | Survey key stakeholders for needs and data visualization suggestions (ie. branding) | TKN, StkHld | 25 | 65 | 1625 |  | 0 | 1625 |  | 1625
3.1.5.2 | Create beta of live dashboard visiualization | SD, UX | 8 | 94 | 752 |  | 0 | 752 |  | 752
3.1.5.3 | Create beta of report manager library | SD, UX | 16 | 94 | 1504 |  | 0 | 1504 |  | 1504
3.1.5.4 | Perform testing of report to validate data | DS | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.6 | SPRINT 1.10 Application Alerts | DS, SE, SD
3.1.7 | Determine triggerable thresholds for basing alerts | DS, PT | 16 | 94 | 1504 |  | 0 | 1504 |  | 1504
3.1.7.1 | Define what data is communicated via alert | DS, PT | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.7.2 | Define frequency for alerts | DS, PT | 8 | 94 | 752 |  | 0 | 752 |  | 752
3.1.7.3 | Define contact population to receive alerts | DS, PT | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.8 | Create alerts | SE, SD | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.8.1 | Perform testing on alert receipt by internal and external parties | DS, SE, SD | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.1.9 | SPRINT 1.11 Data Integration | IT, DS, SE
3.1.9.1 | Confirm IoT MQTT protocol and HTTPS secure web protocol | IT, DS, SE | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.1.9.2 | Confirm JSON initiation events and output messages | IT, DS, SE | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.1.9.3 | Document control of BASIC Script maintenance | IS, IT | 2 | 94 | 188 |  | 0 | 188 |  | 188 | 20525
3.2 | Phase 2 - Data Collection & Analysis
3.2.1 | SPRINT 2.1 Data Connectivity | IS, IT, SE, SD
3.2.2 | Define connectivity between Application and Data Collection Device Cloud Data | IS, IT, SE, SD | 2 | 94 | 188 |  | 0 | 188 |  | 188
3.2.3 | Define data to pull from machines programmable logic controllers (plcs) | IS, IT, SE, SD | 16 | 94 | 1504 |  | 0 | 1504 |  | 1504
3.2.4 | Parse and codify data to be pulled by the data collection device | DS, SE | 8 | 94 | 752 |  | 0 | 752 |  | 752
3.2.5 | Configure data dump/collection into usable metrics display | DS, SD, SE | 16 | 94 | 1504 |  | 0 | 1504 |  | 1504
3.2.6 | SPRINT 2.2 Milestone Confirmation | TKN
3.2.7 | Milestone 1 - supporting metrics for a 1% reduction in scrap | TKN | 1 | 65 | 65 |  | 0 | 65 |  | 65
3.2.8 | Milestone 2 - supporting metrics to determine machine maintenance trends | TKN | 1 | 65 | 65 |  | 0 | 65 |  | 65
3.2.9 | Milestone 3 - confirm sufficient data to being predictive forcasting | TKN | 1 | 65 | 65 |  | 0 | 65 |  | 65
3.2.10 | SPRINT 2.3 Periodic review of database, data storage and collection | DBA, DS
3.2.11 | Collect 1 years worth of data | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520 | 4663
3.3 | Phase 3 - In-house development of data collection device
3.3.1 | SPRINT 3.1 Review knowns to assist in potential unknowns | CE, DS, SE, SD
3.3.2 | Review mapped data tags from eWon Flexy DCD | CE, DS, SE, SD | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.3.3 | Review pain points from eWon Flexy usage | CE | 4 | 94 | 376 |  | 0 | 376 |  | 376
3.3.4 | Develop IIoT application | CE, IS, IT, SE | 2560 | 94 | 240640 |  | 0 | 240640 |  | 240640
3.3.5 | Prepare resolutions to be input into in-house dcd | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
3.3.6 | SPRINT 3.2 Begin plans for in-house dcd application | CE, IS, IT, SE
3.3.7 | Replicate in-house Talk2M | CE, IS, IT, SE | 40 | 94 | 3760 |  | 0 | 3760 |  | 3760
3.3.8 | Configure in-house dcd to application & application interface | CE, IS, IT, SE | 40 | 94 | 3760 |  | 0 | 3760 |  | 3760
3.3.8.1 | SPRINT 3.3 In-house DCD to achieve milestones | TKN
3.3.8.2 | Milestone 1 - supporting metrics for a 1% reduction in scrap | TKN | 1 | 65 | 65 |  | 0 | 65 |  | 65
3.3.8.3 | Milestone 2 - supporting metrics to determine machine maintenance trends | TKN | 1 | 65 | 65 |  | 0 | 65 |  | 65
3.3.8.4 | Milestone 3 - confirm sufficient data to being predictive forcasting | TKN | 1 | 65 | 65 |  | 0 | 65 |  | 65
3.3.9 | SPRINT 3.4 Stress test application | PT
3.4 | SPRINT 3.5 Documentation | TKN
3.5 | Provide internal personel with documented training material | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520
3.6 | Draft new client demonstration of application & reporting packages | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520 | 250407
4 | Phase 4 - Monitor & Controlling
4.1 | Initial Monitor & Control meeting | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
4.1.1 | Determine communication plan (format and frequency) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
4.1.2 | Determine who needs to be communicated to (poss. sub frequency communications based on stakeholder involvement) | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
4.2 | Review eWon Flexy & application testing results | CE | 4 | 94 | 376 |  | 0 | 376 |  | 376
4.2.1 | Review data validation test results | PT | 4 | 94 | 376 |  | 0 | 376 |  | 376
4.2.2 | Review report testing results | DS, SE, SD | 4 | 94 | 376 |  | 0 | 376 |  | 376
4.2.3 | Review security testing results | DBA, IS, IT | 4 | 94 | 376 |  | 0 | 376 |  | 376
4.3 | Document resolutions to failed testing | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
4.4 | Review in-house dcd & application testing results | IS, IT, CE, DS, SD | 4 | 94 | 376 |  | 0 | 376 |  | 376
4.4.1 | Review data validation test results | DS, SE, SD | 4 | 94 | 376 |  | 0 | 376 |  | 376
4.4.2 | Review report testing results | DS, SE, SD | 4 | 94 | 376 |  | 0 | 376 |  | 376
4.4.3 | Review security testing results | IS, IT | 4 | 94 | 376 |  | 0 | 376 |  | 376
4.5 | Document results & version | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
4.6 | Schedule periodic review of in-house dcd & application for poss. enhancements, address user feedback issues | TKN | 4 | 65 | 260 |  | 0 | 260 |  | 260
5 | Phase 5 - Closing
5.1 | Confirm work is done as per requirements | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520
5.2 | Complete the procurement closing process | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520
5.3 | Confirm formal acceptance (based on acceptance criteria noted in scope) | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520
5.4 | Complete final performance reporting documentation | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520
5.5 | Index & archive results | TKN | 2 | 65 | 130 |  | 0 | 130 |  | 130
5.6 | Perform lessons learned meeting | TKN | 8 | 65 | 520 |  | 0 | 520 |  | 520
| Totals |  |  |  | 304777 |  | 0 | 304777 |  | 304777
|  |  |  | SD | 40
|  |  |  | SE | 80
|  |  |  | DS | 100
|  |  |  | UX | 45
|  |  |  | DBA | 150
|  |  |  | CE | 150
94.1667
|  |  |  | IS | 100000
|  |  |  | IT | 65000