## GanttChart
Cober Insights Project Schedule
Cober
| Project Lead: |  | Tom, Komal, Neha
| Project Start Date: |  | 2019-10-21
| Today's Date: |  | 2019-12-13 |  |  |  | [42] | time axis 2020-01-20 to 2020-03-15
| Display Week: |  | 14 | [6 empty] | 2020-01-20: Week 14; 2020-01-27: Week 15; 2020-02-03: Week 16; 2020-02-10: Week 17; 2020-02-17: Week 18; 2020-02-24: Week 19; 2020-03-02: Week 20; 2020-03-09: Week 21
[10 empty] | 2020-01-20 | [6 empty] | 2020-01-27 | [6 empty] | 2020-02-03 | [6 empty] | 2020-02-10 | [6 empty] | 2020-02-17 | [6 empty] | 2020-02-24 | [6 empty] | 2020-03-02 | [6 empty] | 2020-03-09
WBS | Task | Lead | Start | End | Cal Days | % Done | Work Days | Days Done | Days Left | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su
1 | Phase 1 - Initiating (Concept) |  | 2019-10-21 | 2019-11-10 | 21 |  | 15
1.1 | Develop Project Charter | TKN | 2019-10-21 | 2019-11-10 | 21 | 100% | 15 | 21 | 0
1.2 | Identify Stakeholders | TKN | 2019-10-21 | 2019-11-10 | 21 | 100% | 15 | 21 | 0
1.3 | Initiate project documentation | TKN | 2019-10-21 | 2019-11-10 | 21 | 100% | 15 | 21 | 0
1.4 | [Insert new rows above this one, then hide or delete this row]
2 | Phase 2 - Planning |  | 2019-10-21 | 2019-12-31 | 72 |  | 52
2.1 | Team planning meeting | TKN | 2019-10-21 | 2019-10-23 | 3 | 25% | 3 | 0 | 3
2.1.1 | Define sprint schedule | TKN | 2019-10-23 | 2019-10-23 | 1 | 100% | 1 | 1 | 0
2.2 | Scope Management | TKN | 2019-10-25 | 2019-11-04 | 11 | 100% | 7 | 11 | 0
2.2.1 | Prepare and define scope | TKN | 2019-10-25 | 2019-11-04 | 11 | 100% | 7 | 11 | 0
2.3 | Human Resource Management | TKN, HR/MK | 2019-10-24 | 2019-11-06 | 14 | 25% | 10 | 3 | 11
2.3.1 | Identify one System Administrator from current IT staff | HR | 2019-10-25 | 2019-10-30 | 6 | 50% | 4 | 3 | 3
2.3.2 | Hire one additional Computer Engineer | HR | 2019-10-25 | 2019-11-25 | 32 | 25% | 22 | 8 | 24
2.3.3 | Hire one Manufacturing Data Scientist | HR | 2019-10-25 | 2019-11-25 | 32 | 25% | 22 | 8 | 24
2.3.4 | Hire one Software Engineer | HR | 2019-10-25 | 2019-11-25 | 32 | 25% | 22 | 8 | 24 | bar: 2020-01-20 F to 2020-02-24 M; 2020-02-24 Sa
2.3.5 | Hire one Software Developer | HR | 2019-10-25 | 2019-11-25 | 32 | 25% | 22 | 8 | 24
2.3.6 | Hire one UX/UI Designer | HR | 2019-10-25 | 2019-11-25 | 32 | 25% | 22 | 8 | 24
2.3.7 | Hire one Info Security Specialist | HR | 2019-10-25 | 2019-11-25 | 32 | 25% | 22 | 8 | 24
2.3.8 | Schedule First Townhall to introduce project team members | TKN | 2019-11-26 | 2019-11-26 | 1 | 0% | 1 | 0 | 1
2.4 | Collect requirements | TKN | 2019-11-27 | 2019-12-18 | 22 | 0% | 16 | 0 | 22
2.4.1 | Estimate activities requirements (non-labour) | TKN | 2019-11-28 | 2019-12-16 | 19 | 0% | 13 | 0 | 19
2.4.2 | Prepare requirement change request process | TKN | 2019-12-16 | 2019-12-18 | 3 | 0% | 3 | 0 | 3
2.5 | Schedule Management | TKN | 2019-11-26 | 2019-12-11 | 16 | 0% | 12 | 0 | 16
2.5.1 | Review individual resource schedules (ie. vacations, known busy periods...) | TKN | 2019-11-26 | 2019-12-11 | 16 | 15% | 12 | 2 | 14
2.5.2 | Define activities | TKN | 2019-11-29 | 2019-12-18 | 20 | 0% | 14 | 0 | 20
2.5.2.1 | Sequence activities | TKN | 2019-12-02 | 2019-12-18 | 17 | 0% | 13 | 0 | 17
2.5.3 | Identify activities dependencies | TKN | 2019-12-02 | 2019-12-18 | 17 | 0% | 13 | 0 | 17
2.5.4 | Estimate activities resources (labour) | TKN | 2019-12-02 | 2019-12-18 | 17 | 0% | 13 | 0 | 17
2.5.5 | Estimate activities duration | TKN | 2019-12-02 | 2019-12-18 | 17 | 0% | 13 | 0 | 17
2.5.5.1 | Prepare and define schedule | TKN | 2019-12-18 | 2019-12-18 | 1 | 0% | 1 | 0 | 1
2.6 | Prepare estimate of cost baseline | TKN, MK | 2019-12-05 | 2019-12-24 | 20 | 0% | 14 | 0 | 20
2.6.1 | Estimate activities cost (labour and non-labour) | TKN | 2019-12-05 | 2019-12-19 | 1 | 0% | 11 | 0 | 1
2.7 | Risk Management | TKN, MK | 2019-11-07 | 2019-12-15 | 39 | 5% | 27 | 1 | 38
2.7.1 | Prepare risk management questionnaire for brainstorming session | TKN | 2019-11-07 | 2019-11-11 | 5 | 0% | 3 | 0 | 5
2.7.2 | Identify risk | TKN | 2019-11-12 | 2019-12-18 | 37 | 0% | 27 | 0 | 37
2.7.2.1 | Define risk appetite & intolerance | TKN, MK | 2019-11-07 | 2019-11-20 | 14 | 0% | 10 | 0 | 14
2.7.3 | Perform qualitative risk analysis | TKN | 2019-11-12 | 2019-11-25 | 14 | 0% | 10 | 0 | 14
2.7.4 | Perform quantitative risk analysis | TKN, MK | 2019-11-12 | 2019-12-04 | 23 | 0% | 17 | 0 | 23
2.7.5 | Document response plan | TKN | 2019-12-05 | 2019-12-18 | 14 | 0% | 10 | 0 | 14
2.7.6 | Identify possible fallback plan | TKN | 2019-12-05 | 2019-12-18 | 14 | 0% | 10 | 0 | 14
2.8 | Procurement Management | TKN | 2019-12-05 | 2019-12-24 | 20 | 0% | 14 | 0 | 20
2.8.1 | Plan & Conduct third party analysis for external resources (eWon Flexy alternative) | TKN | 2019-12-09 | 2019-12-24 | 16 | 0% | 12 | 0 | 16
2.8.1.1 | Control procurement (manage contract) | TKN | 2019-12-09 | 2019-12-24 | 16 | 0% | 12 | 0 | 16
2.8.1.2 | Close procurement (ensure proper execution of contract) | TKN | 2019-12-09 | 2019-12-24 | 16 | 0% | 12 | 0 | 16
2.8.2 | Plan & Conduct third party analysis for external resources (Azure) | TKN | 2019-12-09 | 2019-12-24 | 16 | 0% | 12 | 0 | 16
2.8.2.1 | Control procurement (manage contract) | TKN | 2019-12-09 | 2019-12-24 | 16 | 0% | 12 | 0 | 16
2.8.2.2 | Close procurement (ensure proper execution of contract) | TKN | 2019-12-09 | 2019-12-24 | 16 | 0% | 12 | 0 | 16
2.9 | Milestone Mapping | TKN | 2019-12-05 | 2019-12-24 | 20 | 0% | 14 | 0 | 20
2.9.1 | Survey project team for possible milestone identifiers | TKN | 2019-12-09 | 2019-12-24 | 16 | 0% | 12 | 0 | 16
2.10 | [Insert new rows above this one, then hide or delete this row]
3 | Phase 3 - Executing (Designing, Implementation (& build), Testing) |  | 2020-01-01 | 2022-06-30 | 912 |  | 652 | bar: 2020-01-20 M to 2020-03-09 Su
3.1 | Phase 1 - Architecture |  | 2020-01-01 | 2020-03-31 | 91 | 0% | 65 | 0 | 91 | bar: 2020-01-20 M to 2020-03-09 Su
3.1.1 | Meeting to discuss stakeholder needs and concerns with architecture (ie. security, reporting templates...) | TKN, StkHld | 2020-01-02 | 2020-01-09 | 8 | 98% | 6 | 7 | 1 | bar: 2020-03-09 F
3.1.1.1 | Meeting to discuss high level connections | IS, IT | 2020-01-09 | 2020-01-16 | 8 | 98% | 6 | 7 | 1 | bar: 2020-03-09 F
3.1.2 | SPRINT 1.1 Cloud Architecture | IS, IT |  |  | 1 | 16% | 0 | 0 | 1 | bar: 2020-03-09 F
3.1.2.1 | Define single connectivity between eWon Flexy and Azure Iot Hub MQTT | IT, CE | 2020-01-13 | 2020-01-20 | 8 | 15% | 6 | 1 | 7 | bar: 2020-01-20 M; 2020-03-09 F
3.1.2.2 | Define multiple connectivity between eWon Flexy and Azure Iot Hub MQTT (as Cober has multiple clients with multiple machines...) | IT, CE | 2020-01-13 | 2020-01-20 | 8 | 14% | 6 | 1 | 7 | bar: 2020-01-20 M; 2020-03-09 F
3.1.2.3 | Test message relay between eWon Flexy and Azure Iot Hub MQTT | IT | 2020-01-13 | 2020-01-20 | 8 | 0% | 6 | 0 | 8 | bar: 2020-01-20 M; 2020-03-09 F
3.1.2.4 | Define security protocols for multi connectivity to ensure client data confidentiality | IS, IT | 2020-01-11 | 2020-01-30 | 20 | 0% | 14 | 0 | 20 | bar: 2020-01-20 M to 2020-01-27 Th; 2020-03-09 F
3.1.2.5 | SPRINT 1.2 Cloud to App Connection | IS, IT, DS | 2020-01-20 | 2020-02-14 | 26 | 0% | 20 | 0 | 26 | bar: 2020-01-20 M to 2020-02-10 F; 2020-03-09 F
3.1.2.6 | Map data parsing channels from Azure IoT Hub to Azure Service Bus | IS, IT, DS | 2020-01-20 | 2020-02-14 | 26 | 0% | 20 | 0 | 26 | bar: 2020-01-20 M to 2020-02-10 F; 2020-03-09 F
3.1.2.7 | Map data parsing channels from Azure IoT Hub to Stream Anayltics Job | IS, IT, DS | 2020-01-20 | 2020-02-14 | 26 | 0% | 20 | 0 | 26 | bar: 2020-01-20 M to 2020-02-10 F; 2020-03-09 F
3.1.2.8 | Map data parsing channels from Azure IoT Hub to Blob Storage | IS, IT, DS | 2020-01-20 | 2020-02-14 | 26 | 0% | 20 | 0 | 26 | bar: 2020-01-20 M to 2020-02-10 F; 2020-03-09 F
3.1.2.9 | Define Azure Service Bus connection to Logic Apps & Email functions | IS, IT, CE | 2020-01-24 | 2020-01-30 | 7 | 0% | 5 | 0 | 7 | bar: 2020-01-20 F to 2020-01-27 Th; 2020-03-09 F
3.1.2.10 | Define Stream Analytics Jobs to Power BI's Live Dashboards | IS, IT, CE | 2020-01-24 | 2020-01-30 | 7 | 0% | 5 | 0 | 7 | bar: 2020-01-20 F to 2020-01-27 Th; 2020-03-09 F
3.1.2.11 | Define Power BI's Live Dashboards connectivity with Blob Storage and SQL/App Service | IS, IT, CE | 2020-01-24 | 2020-01-30 | 7 | 0% | 5 | 0 | 7 | bar: 2020-01-20 F to 2020-01-27 Th; 2020-03-09 F
3.1.3 | SPRINT 1.3 SQL DB Architecture | DBA | 2020-01-30 | 2020-02-16 | 18 | 0% | 12 | 0 | 18 | bar: 2020-01-27 Th to 2020-02-10 Su; 2020-03-09 F
3.1.3.1 | Review E-R Model, SQL DB and Job Scheduler | DBA, CE | 2020-01-31 | 2020-02-07 | 8 | 0% | 6 | 0 | 8 | bar: 2020-01-27 F to 2020-02-03 F; 2020-03-09 F
3.1.3.2 | Configure SQL DB with Cober Data Analytics Flask Webapp | DBA, CE | 2020-02-07 | 2020-02-17 | 11 | 0% | 7 | 0 | 11 | bar: 2020-02-03 F to 2020-02-17 M; 2020-03-09 F
3.1.3.3 | Configure basic SQL reports based on internal expertise input (ie. what would machine tech's want to see) | DBA, CE | 2020-02-07 | 2020-02-17 | 11 | 0% | 7 | 0 | 11 | bar: 2020-02-03 F to 2020-02-17 M; 2020-03-09 F
3.1.3.4 | SPRINT 1.4 Security Assignment | IS, IT, DBA | 2020-02-17 | 2020-02-21 | 5 | 0% | 5 | 0 | 5 | bar: 2020-02-17 M to 2020-02-17 F; 2020-03-09 F
3.1.3.5 | Assign personel to cloud security | IS, IT | 2020-01-10 | 2020-01-13 | 4 | 0% | 2 | 0 | 4 | bar: 2020-03-09 F
3.1.3.6 | Assign personel as DBMA | IS, IT | 2020-01-10 | 2020-01-13 | 4 | 0% | 2 | 0 | 4 | bar: 2020-03-09 F
3.1.3.7 | Define security change management protocol | IS, IT, DBA | 2020-02-17 | 2020-02-21 | 5 | 0% | 5 | 0 | 5 | bar: 2020-02-17 M to 2020-02-17 F; 2020-03-09 F
3.1.3.8 | SPRINT 1.5 Perform security testing | IS, IT, DBA, CE, PT | 2020-02-17 | 2020-02-26 | 10 | 0% | 8 | 0 | 10 | bar: 2020-02-17 M to 2020-02-24 W; 2020-03-09 F
3.1.4 | SPRINT 1.6 App Access Right Config | IT, SD, SE, UX | 2020-02-17 | 2020-03-05 | 18 | 0% | 14 | 0 | 18 | bar: 2020-02-17 M to 2020-03-02 Th; 2020-03-09 F
3.1.4.1 | Determine population for the following security access levels Global Administrator, Company Administrator, Regular User | IT, SD, UX | 2020-02-17 | 2020-02-20 | 4 | 0% | 4 | 0 | 4 | bar: 2020-02-17 M to 2020-02-17 Th; 2020-03-09 F
3.1.4.2 | Determine security access level rights (add, remove users, restrict views, export functionality) | IS, IT | 2020-02-20 | 2020-02-25 | 6 | 0% | 4 | 0 | 6 | bar: 2020-02-17 Th to 2020-02-24 T; 2020-03-09 F
3.1.4.3 | SPRINT 1.7 Data to Application config | CE, DS, SE, SD | 2020-02-21 | 2020-02-26 | 6 | 0% | 4 | 0 | 6 | bar: 2020-02-17 F to 2020-02-24 W; 2020-03-09 F
3.1.4.4 | Identification of data tags (service bus, blob storage, Power BI Rest API) | DS | 2020-02-21 | 2020-02-26 | 6 | 0% | 4 | 0 | 6 | bar: 2020-02-17 F to 2020-02-24 W; 2020-03-09 F
3.1.4.5 | Perform data tag formatting testing to identify breaks | CE, DS, SE, SD | 2020-02-21 | 2020-02-26 | 6 | 0% | 4 | 0 | 6 | bar: 2020-02-17 F to 2020-02-24 W; 2020-03-09 F
3.1.5 | SPRINT 1.8 App User Interface Configuration- Functional Specifications & Testing | SD, UX | 2020-02-17 | 2020-02-26 | 10 | 0% | 8 | 0 | 10 | bar: 2020-02-17 M to 2020-02-24 W; 2020-03-09 F
3.1.5.1 | Survey key stakeholders for needs and data visualization suggestions (ie. branding) | TKN, StkHld | 2020-02-17 | 2020-02-20 | 4 | 0% | 4 | 0 | 4 | bar: 2020-02-17 M to 2020-02-17 Th; 2020-03-09 F
3.1.5.2 | Create beta of live dashboard visiualization | SD, UX | 2020-02-20 | 2020-03-04 | 14 | 0% | 10 | 0 | 14 | bar: 2020-02-17 Th to 2020-03-02 W; 2020-03-09 F
3.1.5.3 | Create beta of report manager library | SD, UX | 2020-02-20 | 2020-03-04 | 14 | 0% | 10 | 0 | 14 | bar: 2020-02-17 Th to 2020-03-02 W; 2020-03-09 F
3.1.5.4 | Perform testing of report to validate data | DS | 2020-02-28 | 2020-03-08 | 10 | 0% | 6 | 0 | 10 | bar: 2020-02-24 F to 2020-03-02 Su; 2020-03-09 F
3.1.6 | SPRINT 1.9 Application Alerts | DS, SE, SD | 2020-02-17 | 2020-02-24 | 8 | 0% | 6 | 0 | 8 | bar: 2020-02-17 M to 2020-02-24 M; 2020-03-09 F
3.1.7 | Determine triggerable thresholds for basing alerts | DS, PT | 2020-02-17 | 2020-02-24 | 8 | 0% | 6 | 0 | 8 | bar: 2020-02-17 M to 2020-02-24 M; 2020-03-09 F
3.1.7.1 | Define what data is communicated via alert | DS, PT | 2020-02-17 | 2020-02-24 | 8 | 0% | 6 | 0 | 8 | bar: 2020-02-17 M to 2020-02-24 M; 2020-03-09 F
3.1.7.2 | Define frequency for alerts | DS, PT | 2020-02-17 | 2020-02-24 | 8 | 0% | 6 | 0 | 8 | bar: 2020-02-17 M to 2020-02-24 M; 2020-03-09 F
3.1.7.3 | Define contact population to receive alerts | DS, PT | 2020-02-17 | 2020-02-24 | 8 | 0% | 6 | 0 | 8 | bar: 2020-02-17 M to 2020-02-24 M; 2020-03-09 F
3.1.8 | Create alerts | SE, SD | 2020-02-17 | 2020-02-24 | 8 | 0% | 6 | 0 | 8 | bar: 2020-02-17 M to 2020-02-24 M; 2020-02-24 Sa; 2020-03-09 F
3.1.8.1 | Perform testing on alert receipt by internal and external parties | DS, SE, SD | 2020-02-26 | 2020-03-06 | 10 | 0% | 8 | 0 | 10 | bar: 2020-02-24 W to 2020-03-02 F; 2020-03-09 F
3.1.9 | SPRINT 1.10 Data Integration | IT, DS, SE | 2020-03-06 | 2020-04-15 | 41 | 0% | 29 | 0 | 41 | bar: 2020-03-02 F to 2020-03-09 Su
3.1.9.1 | Confirm IoT MQTT protocol and HTTPS secure web protocol | IT, DS, SE | 2020-04-10 | 2020-04-16 | 7 | 0% | 5 | 0 | 7 | bar: 2020-03-09 F
3.1.9.2 | Confirm JSON initiation events and output messages | IT, DS, SE | 2020-04-10 | 2020-04-16 | 7 | 0% | 5 | 0 | 7 | bar: 2020-03-09 F
3.1.9.3 | Document control of BASIC Script maintenance | IS, IT | 2020-03-15 | 2020-05-14 | 61 | 0% | 44 | 0 | 61 | bar: 2020-03-09 F; 2020-03-09 Su
3.2 | Phase 2 - Data Collection & Analysis |  | 2020-04-01 | 2021-06-30 | 456 | 0% | 326 | 0 | 456
3.2.1 | SPRINT 2.1 Data Connectivity | IS, IT, SE, SD | 2020-04-01 | 2020-05-11 | 41 | 0% | 29 | 0 | 41 | bar: 2020-02-17 Su
3.2.2 | Define connectivity between Application and Data Collection Device Cloud Data | IS, IT, SE, SD | 2020-04-01 | 2020-04-08 | 8 | 0% | 6 | 0 | 8
3.2.3 | Define data to pull from machines programmable logic controllers (plcs) | IS, IT, SE, SD | 2020-04-06 | 2020-04-13 | 8 | 0% | 6 | 0 | 8
3.2.4 | Parse and codify data to be pulled by the data collection device | DS, SE | 2020-04-14 | 2020-05-01 | 18 | 0% | 14 | 0 | 18
3.2.5 | Configure data dump/collection into usable metrics display | DS, SD, SE | 2020-04-15 | 2020-05-11 | 27 | 0% | 19 | 0 | 27
3.2.6 | SPRINT 2.2 Milestone Confirmation | TKN | 2020-05-05 | 2020-06-30 | 57 | 0% | 41 | 0 | 57 | bar: 2020-02-17 Su
3.2.7 | Milestone 2 - supporting metrics to determine machine maintenance trends | TKN | 2020-05-20 | 2020-06-30 | 42 | 0% | 30 | 0 | 42
3.2.8 |  | TKN | 2020-05-20 | 2020-06-30 | 42 | 0% | 30 | 0 | 42
3.2.9 | Milestone 3 - confirm sufficient data to being predictive forcasting | TKN | 2020-05-20 | 2020-06-30 | 42 | 0% | 30 | 0 | 42 | bar: 2020-03-09 Th
3.2.10 | SPRINT 2.3 Periodic review of database, data storage and collection | DBA, DS | 2020-05-15 | 2021-06-30 | 412 | 0% | 294 | 0 | 412 | bar: 2020-03-09 Th
3.2.11 | Collect 1 years worth of data | TKN | 2020-05-15 | 2021-06-30 | 412 | 0% | 294 | 0 | 412 | bar: 2020-03-09 Th
3.3 | Phase 3 - In-house development of data collection device |  | 2020-07-01 | 2020-12-31 | 184 | 0% | 132 | 0 | 184
3.3.1 | SPRINT 3.1 Review knowns to assist in potential unknowns | CE, DS, SE, SD | 2020-07-01 | 2020-08-03 | 34 | 0% | 24 | 0 | 34 | bar: 2020-02-17 Su
3.3.2 | Review mapped data tags from eWon Flexy DCD | CE, DS, SE, SD | 2020-07-01 | 2020-08-03 | 34 | 0% | 24 | 0 | 34
3.3.3 | Review pain points from eWon Flexy usage | CE | 2020-07-01 | 2020-08-03 | 34 | 0% | 24 | 0 | 34
3.3.4 | Develop IIoT application | CE, IS, IT, SE | 2020-07-01 | 2020-08-03 | 34 | 0% | 24 | 0 | 34
3.3.5 | Prepare resolutions to be input into in-house dcd | TKN | 2020-08-04 | 2020-09-15 | 43 | 0% | 31 | 0 | 43 | bar: 2020-03-09 Th
3.3.6 | SPRINT 3.2 Begin plans for in-house dcd application | CE, IS, IT, SE | 2020-09-15 | 2020-10-30 | 46 | 0% | 34 | 0 | 46 | bar: 2020-02-17 Su; 2020-03-09 Th
3.3.7 | Replicate in-house Talk2M | CE, IS, IT, SE | 2020-08-04 | 2020-09-15 | 43 | 0% | 31 | 0 | 43 | bar: 2020-03-09 Th
3.3.8 | Configure in-house dcd to application & application interface | CE, IS, IT, SE | 2020-09-15 | 2020-11-02 | 49 | 0% | 35 | 0 | 49 | bar: 2020-03-09 Th
3.3.8.1 | SPRINT 3.3 In-house DCD to achieve milestones | TKN | 2020-11-02 | 2021-03-31 | 150 | 0% | 108 | 0 | 150 | bar: 2020-02-17 Su
3.3.8.2 | Milestone 1 - supporting metrics for a 1% reduction in scrap | TKN | 2020-10-30 | 2021-03-31 | 153 | 0% | 109 | 0 | 153
3.3.8.3 | Milestone 2 - supporting metrics to determine machine maintenance trends | TKN | 2020-10-30 | 2021-03-31 | 153 | 0% | 109 | 0 | 153
3.3.8.4 | Milestone 3 - confirm sufficient data to being predictive forcasting | TKN | 2020-10-30 | 2021-03-31 | 153 | 0% | 109 | 0 | 153
3.3.9 | SPRINT 3.4 Stress test application | PT | 2020-09-30 | 2021-04-25 | 208 | 0% | 148 | 0 | 208 | bar: 2020-03-09 Th
3.4 | SPRINT 3.5 Documentation | TKN | 2021-04-01 | 2021-06-30 | 91 | 0% | 65 | 0 | 91 | bar: 2020-02-17 Su
3.5 | Provide internal personel with documented training material | TKN | 2021-04-01 | 2021-06-30 | 91 | 0% | 65 | 0 | 91
3.6 | Draft new client demonstration of application & reporting packages | TKN | 2021-04-01 | 2021-06-30 | 91 | 0% | 65 | 0 | 91
3.7 | [Insert new rows above this one, then hide or delete this row]
4 | Phase 4 - Monitor & Controlling |  | 2019-10-21 | 2021-06-30 | 619 |  | 443 | bar: 2020-01-20 M to 2020-03-09 Su
4.1 | Initial Monitor & Control meeting | TKN | 2019-10-21 | 2019-11-15 | 26 | 0% | 20 | 0 | 26
4.1.1 | Determine communication plan (format and frequency) | TKN | 2020-01-01 | 2020-01-31 | 31 | 0% | 23 | 0 | 31 | bar: 2020-01-20 M to 2020-01-27 F
4.1.2 | Determine who needs to be communicated to (poss. sub frequency communications based on stakeholder involvement) | TKN | 2020-01-01 | 2020-01-31 | 31 | 0% | 23 | 0 | 31 | bar: 2020-01-20 M to 2020-01-27 F
4.2 | Review eWon Flexy & application testing results | CE | 2020-06-01 | 2020-06-20 | 20 | 0% | 15 | 0 | 20
4.2.1 | Review data validation test results | PT | 2020-06-01 | 2020-06-20 | 20 | 0% | 15 | 0 | 20
4.2.2 | Review report testing results | DS, SE, SD | 2020-06-01 | 2020-06-20 | 20 | 0% | 15 | 0 | 20
4.2.3 | Review security testing results | DBA, IS, IT | 2020-06-01 | 2020-06-20 | 20 | 0% | 15 | 0 | 20 | bar: 2020-03-09 Th
4.3 | Document resolutions to failed testing | TKN | 2020-06-19 | 2020-06-30 | 12 | 0% | 8 | 0 | 12 | bar: 2020-03-09 Th
4.4 | Review in-house dcd & application testing results | IS, IT, CE, DS, SD | 2020-11-02 | 2021-01-15 | 75 | 0% | 55 | 0 | 75
4.4.1 | Review data validation test results | DS, SE, SD | 2020-11-02 | 2021-01-15 | 75 | 0% | 55 | 0 | 75
4.4.2 | Review report testing results | DS, SE, SD | 2020-11-02 | 2021-01-15 | 75 | 0% | 55 | 0 | 75
4.4.3 | Review security testing results | IS, IT | 2020-11-02 | 2021-01-15 | 75 | 0% | 55 | 0 | 75 | bar: 2020-03-09 Th
4.5 | Document results & version | TKN | 2021-01-18 | 2021-02-26 | 40 | 0% | 30 | 0 | 40
4.6 | Schedule periodic review of in-house dcd & application for poss. enhancements, address user feedback issues | TKN | 2021-03-01 | 2021-03-15 | 15 | 50% | 11 | 7 | 8 | bar: 2020-03-09 Th
4.7 | [Insert new rows above this one, then hide or delete this row]
5 | Phase 5 - Closing |  | 2021-03-16 | 2021-06-30 | 107 |  | 77
5.1 | Confirm work is done as per requirements | TKN | 2021-03-16 | 2021-06-15 | 92 | 0% | 66 | 0 | 92
5.2 | Complete the procurement closing process | TKN | 2021-03-19 | 2021-06-01 | 75 | 0% | 53 | 0 | 75
5.3 | Confirm formal acceptance (based on acceptance criteria noted in scope) | TKN | 2021-06-01 | 2021-06-15 | 15 | 0% | 11 | 0 | 15
5.4 | Complete final performance reporting documentation | TKN | 2021-06-15 | 2021-06-25 | 11 | 0% | 9 | 0 | 11
5.5 | Index & archive results | TKN | 2021-06-23 | 2021-06-25 | 3 | 0% | 3 | 0 | 3
5.6 | Perform lessons learned meeting | TKN | 2021-06-28 | 2021-06-30 | 3 | 0% | 3 | 0 | 3
5.7 | [Insert new rows above this one, then hide or delete this row]
TEMPLATE ROWS
See the Help worksheet for information about using template rows.
1 | [ Task Category (label only) ]
2 | [ Task Category (summary) ] |  | 2019-10-21 | 2019-10-21 | 1 |  | 1
2.1 | [ Level 2 Task ] |  | 2019-10-21 | 2019-10-21 | 1 | 0% | 1 | 0 | 1
2.1.1 | . [ Level 3 Task ] |  | 2019-10-21 | 2019-10-21 | 1 | 0% | 1 | 0 | 1
2.1.1.1 | . . [ Level 4 Task ] |  | 2019-10-21 | 2019-10-21 | 1 | 0% | 1 | 0 | 1

## Lead Key
Lead Short Code | Lead Description | Role Description
TKN | Tom Komal Neha | The best PM's in J Currey's class
HR | Human Resources | Hiring & Firing
IS | Information Security | Secure technology from threats, cloud security
IT | IT System Administrator | Tech support, deployments, updates, etc.
CE | Computer Engineer | Computer hardware professional (build the in house dcd)
DS | Data Scientist | Big data and analytics specialist
SD | Software Developer | Specializes in creating software
SE | Software Engineer
UX | UX/UI Designer | Specializes in human interaction with software
StkHld | Stakeholder(s) | those affected by the project
MK | Matthew Krieger (project sponsor) | Actual Cober, Inc. VP of technology
PT | selected resources from departments to make up project team | project team
DBA | Database administrator | database design, implementation, maintenance, support
Completed
In progress (not completed)

## Help
Help |  | © 2012-2018 Vertex42 LLC
Contact Vertex42
Introduction
This Gantt Chart spreadsheet makes creating a project schedule very easy. You only need to know some basic spreadsheet operations to make this gantt chart work for you, such as how to insert, delete, copy and paste entire rows.
Be sure to read the Getting Started Tips below.
The Share settings for this spreadsheet must always be set to "Private"
See the TermsOfUse worksheet for more information about how you may or may not share this template.
Getting Started Tips
- | Input cells for defining the task dates and durations have a light green background. | Input Cell
- | [ Bracketed Text ] is also meant to be edited, like the project title and task descriptions.
- | Some of the labels include cell notes to provide extra help information. | Label
- | The Project Start Date determines the first week shown in the gantt chart.
- | To adjust the range of dates shown in the gantt chart, change the Display Week.
- | The red line in the gantt chart represents the date in the Today's Date cell. You can enter Today's Date manually or use the formula =TODAY()
- | To insert a new task, insert a new row, then copy/paste an existing row from the selection of Template Rows at the bottom of the worksheet.
- | Edit the Holidays worksheet to choose which dates you want to exclude from Work Days.
Cell Color Key
Input Cell :: Indicates which set of inputs to use
Completed Task :: In the Gantt chart, indicates the completed portion of the task
Incomplete Task :: In the Gantt chart, indicates the incomplete portion of the task
Using the Template Rows and Choosing a WBS Level
Inserting New Tasks
1. Insert a new blank row where you want the new task to be
2. Copy the entire row you want to use from the set of template rows
3. Paste the row you copied on top of the blank row you just inserted
4. Copy and paste the WBS cell separately, based on the level (1, 2.1, 3.2.1, 4.3.2.1)
- When inserting new rows, you must copy and paste an entire row, because the cells of the Gantt chart area are formulas.
Changing the WBS Level in the WBS Column
- The WBS numbering uses a different formula for each level, but the formula does not reference any other cell in the row. So, you can copy and paste just the WBS cell that you want to use.
- If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter them if you need to.
- You can indent the task description for sub-tasks by entering spaces (until Google decides to add an indent option).
Category Tasks
- You can use tasks that are just labels, but it can be even more useful for a category task to display the minimum Start date and maximum End date of its sub tasks. This can be done using =MIN(range_of_startdates) and =MAX(range_of_enddates). An example template row is provided, but you will need to update the MIN() and MAX() formulas.
Creating Task Dependencies
- You can enter the Start date manually, or define task dependecies using a formula. Below are the most common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
- Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
- For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
- This formula is very simple: =enddate+1
- For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3 )+1
E. | Set the Start date to a number of days before or after another date.
- This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
FAQs
Q: | What is the best way to Print?
A: | First, select all of the rows you want to print. Then, in the Print Settings, choose "Selection" and check "No Gridlines". Fit to width and print in landscape.
You also may want to hide the Days Done, Days Left, and Color columns prior to printing.
Q: | How do I only show Monday-Friday in the chart area?
A: | You can hide the columns that show the weekends.
Q: | How do I print the entire range of dates for my project?
A: | You would first need to add more columns to the displayed chart area. You can insert more columns to the right of the chart area and then copy and paste columns (7 at a time) to extend the display.
Note: The more columns you add to the right of the Gantt chart, the slower the recalculation speed will be, because of the number of additional formulas.
Q: | How do I calculate the %Complete for a Summary task?
A: | The %Complete for a summary task can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work days and "complete" is a reference to the %complete for each of the subtasks.
=ARRAYFORMULA( SUMPRODUCT( workdays, complete ) / SUM ( workdays ) )
Q: | The Start date, End date, or %Complete for a Level 1 task is wrong. How do I fix it?
A: | When using =MIN(), =MAX(), and =SUMPRODUCT(), it is easy for the references to get messed up if you move rows around or insert new rows. You should verify and fix these formulas if they are not referencing the correct ranges.
Q: | I've messed up the chart area somehow. How do I fix it?
A: | Find a row that works, then copy the cells that make up the gantt chart area from that row into the cells that are messed up.

## GanttChartPro
Gantt Chart Template Pro for Google Sheets
Gantt Chart Template Pro, by Vertex42.com, is a spreadsheet template designed originally for Microsoft Excel that offers more features than the free version. When you purchase it, you will also get a link to download the Pro version for Google Sheets!!
Learn More About Gantt Chart Template Pro
- Visit the web page above to view screenshots and watch demo videos
Features in the Pro version for Google Sheets
Define task durations by specifying the number of Work Days
- In this free version, the inputs to define a task are the Start Date and the Calendar Day duration. In the Pro version, the default option is to enter the Start Date and the number of Work Days.
Choose whether to define task durations using Calendar Days or Work Days or End Dates
- The Pro version includes a larger set of template rows that provide more options for defining the Start date, End date, duration, and dependency of tasks.
Exclude holidays from work days
- List holidays and other non-working days in a separate sheet. When defining task durations using Work Days, these dates will be excluded.
Define what you mean by "Weekend" when using Work Days
- The Pro version allows you to define exactly which day(s) of the week you want to use as your weekend. The default is Saturday and Sunday.
Color-Code bars in the Gantt chart
- The Pro version includes a column for entering a color code like "k", "r", or "y" to change the color of the bars in the Gantt chart. The Help worksheet explains some advanced formulas that you could use in the Color column to automatically color a bar based on the name in the Lead column.
Define tasks dependences by specifying the predecessor WBS
- The template rows include an option for entering a Predecessor WBS. The Start date will be calculated as the day following the End date of the predecessor.

## TermsOfUse
Terms of Use
Gantt Chart Template for Google Sheets
© 2012-2018 Vertex42 LLC. All rights reserved.
This template is a copyrighted work under the Unites States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
The Share Settings for this spreadsheet must always be set to "Private"
Limited Private Sharing and Other Allowed Uses
See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html

## © (hidden)
Gantt Chart Template
© 2012-2014 Vertex42 LLC
Please note the Terms Of Use
http://www.vertex42.com/licensing/EULA_privateuse.html