## Matrix
RACI Matrix | [14 empty] | Roles and Responsibilities
Cober Insights | [14 empty] | Responsible, Accountable, Consulted, Informed | RACI Matrix Template
© 2018 Vertex42.com
|  | ROLES | Matthew Krieger | Project Team | Human Resources | Info Sec (IS) | IT | Computer Engineer (CE) | Data Scientist (DS) | Database Administrator (DBA) | Software Engineer (SE) | Software Developer (SD) | UX Designer (UX) | Cober Technichians | Trail Clients | ◄ Insert more roles by inserting new columns
| Deliverable or Task | Status | Sponsor / Leadership |  | Other Resources | [10 empty] | ◄ Edit role categories to aid in organization
Phase 1 - Initiating
| Develop project charter |  | D | A | [11 empty] | Edit color-coding via Home > Conditional Formatting
| Perform stakeholder analysis |  | D | A
| Initiate project documentation |  | D | A
| Phase 2 - Planning | [14 empty] | To clear the sample set of data, select cells and press Delete
| Requirements collection |  | A | R | S
| Resource Management |  | D | R | A
| Hire additional staff |  | I | A | R
| Revisit requirements (hardware, software based on feedback from consulted staff) |  | I | R | S | C | C | C | C | C | C | C | C | C
Schedule Management | bar: I I to A R
Defining sprint schedule | bar: A R
| Cost estimation |  | A | R | C | S | S | S | S | S | S | S | S | S
| Risk Management |  | A | R | I | I | I | I | I | I | I | I | I | I
Procurement Management | bar: R R to R S
| Milestone Mapping |  | D | R |  | C | C | C | C | C | C | C | C | I
Phase 3 - Executing
| Stakeholder Meeting |  | D | A | C | C | C | C | C | C | C | C | C | I | C
| Cloud Architecure |  | D: I; A: D; C: R; C: S
| Define single connectivity between eWon Flexy and Azure Iot Hub MQTT |  | A: D; C: S; C: A; C: R
| Define multiple connectivity between eWon Flexy and Azure Iot Hub MQTT (as Cober has multiple clients with multiple machines...) |  | A: D; C: S; C: A; C: R
| Test message relay between eWon Flexy and Azure Iot Hub MQTT |  | A: D; C: A; C: R
| Define security protocols for multi connectivity to ensure client data confidentiality |  | A: D; C: A; C: R
| Cloud to App Connection |  | D: I; A: D; C: A; C: R; C: R
| Map data parsing channels from Azure IoT Hub to Azure Service Bus |  | A: D; C: S; C: A; C: C; C: R
| Map data parsing channels from Azure IoT Hub to Stream Anayltics Job |  | A: D; C: S; C: A; C: C; C: R
| Map data parsing channels from Azure IoT Hub to Blob Storage |  | A: D; C: S; C: A; C: C; C: R
| Define Azure Service Bus connection to Logic Apps & Email functions |  | A: D; C: S; C: A; C: C; C: R
| Define Stream Analytics Jobs to Power BI's Live Dashboards |  | A: D; C: S; C: A; C: C; C: R
| Define Power BI's Live Dashboards connectivity with Blob Storage and SQL/App Service |  | A: D; C: S; C: A; C: C; C: R
| SQL DB Architecture |  | I | D |  | I | I | C | I | A | I | I
| Review E-R Model, SQL DB and Job Scheduler |  | A: D; C: C; C: R
| Configure SQL DB with Cober Data Analytics Flask Webapp |  | A: D; C: C; C: R
| Configure basic SQL reports based on internal expertise input (ie. what would machine tech's want to see) |  | A: D; C: C; C: R
| Security Assignment |  | A: D; C: A; C: R; C: I; C: C; I: I
| Assign personel to cloud security |  | A: D; C: A; C: R; C: I; C: I; C: I
| Assign personel as DBMA |  | A: D; C: A; C: R; C: I; C: I; C: I
| Define security change management protocol |  | A: D; C: A; C: R; C: I; C: I; C: I
| Security Testing |  | A: D; C: S; C: A; C: S; C: S
| App Access Right Config |  |  | D |  | C | A | I |  |  | S | C | C | I
| Determine population for the following security access levels Global Administrator, Company Administrator, Regular User |  | C: C; C: R; C: I; C: S; C: C; C: C; I: I
| Determine security access level rights (add, remove users, restrict views, export functionality) |  | C: A; C: R; C: I; C: S; C: C; C: C; I: I
| Data to App Config |  |  | D |  | S | C | A | C | C | S |  |  | I
| Identification of data tags (service bus, blob storage, Power BI Rest API) |  | A: D; C: R; C: A; C: S
| Perform data tag formatting testing to identify breaks |  | A: D; C: S; C: A; C: S
| App User Interface Config |  | D | R |  |  | S | S | S | R | C | S | R
| Survey key stakeholders for needs and data visualization suggestions (ie. branding) |  | D | A |  |  | S | S | S | I | S | S | R | I | I
| Create beta of live dashboard visiualization |  |  | D |  |  | S | S | S | R | S | S | A | S
| Create beta of report manager library |  |  | D |  |  | S | S | S | R | S | S | A | S
| Perform testing of report to validate data |  |  | D |  |  | S | S | S | R | S | S | A | S
| Application Alerts |  |  | D |  |  | S | S | A | C | C | R |  | C | I
| Determine triggerable thresholds for basing alerts |  | A: D; C: R; C: S; C: I; I: R
| Define what data is communicated via alert |  |  | D |  |  | S | S | A | C | C | R |  | C | I
| Define frequency for alerts |  |  | D |  |  | S | S | A | C | C | R |  | C
| Define contact population to receive alerts |  |  | D |  |  | S | S | A | C | C | R |  | C
| Create alerts |  |  | D |  |  | S | S | A | C | C | R |  | C
| Perform testing on alert receipt by internal and external parties |  |  | D |  |  | S | S | A | C | C | R |  | C
| Data Integration |  | A: D; C: S; C: R; C: A
| Confirm IoT MQTT protocol and HTTPS secure web protocol |  | A: D; C: A; C: C; C: R; C: R; C: S
| Confirm JSON initiation events and output messages |  | A: D; C: A; C: C; C: R; C: R; C: S
| Document control of BASIC Script maintenance |  | A: D; C: R; C: A
| Data Connectivity |  |  | D |  | S | R | S | R |  | A | I |  | R
| Define connectivity between Application and Data Collection Device Cloud Data |  | C: S; C: R; C: R; C: A
Define data to pull from machines programmable logic controllers (plcs) | bar: C to C; I
| Parse and codify data to be pulled by the data collection device |  | C: S; C: A; C: S; C: S; I: C
| Configure data dump/collection into usable metrics display |  | C: I; C: R; C: A; C: R; C: I; I: C
| Milestone Confirmation |  | A | R |  | C | C | C | C | C | C | C | C | I
| Milestone 1 - supporting metrics for a 1% reduction in scrap |  |  | R |  | C | C | C | R | C | C | C | C | A
| Milestone 2 - supporting metrics to determine machine maintenance trends |  |  | R |  | C | C | C | C | C | C | C | C | A
| Milestone 3 - confirm sufficient data to being predictive forcasting |  |  | R |  | C | C | C | A | C | C | C | C | R
| Database review |  | A: D; C: I; C: S; C: A; C: I
Collect 1 years worth of data
| Phase 3 - In-house development of data collection device |  | A | D |  | S | S | R | S | I | S | I | I | C | I
Phase 4 - Monitor & Controlling
| Monitor & Control |  | I | A | bar: S to I
| QA review (multiple tasks rolled up) |  |  |  |  | A | S | A | S | A | A | S | A | S | I
Phase 5 - Closing
| Perform project closing checklist |  | A | D | bar: S to C
Insert new rows above this one
D | Driver | Assists those who are responsible for a task. | [13 empty] | ◄ Delete unneeded rows to remove from the drop-down lists
R | Responsible | Assigned to complete the task or deliverable. | [13 empty] | ◄ Edit the table of abbreviations and definitions as needed
A | Accountable | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Support | Provides support during implementation.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.

## About
RACI MATRIX TEMPLATE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/raci-matrix.html
© 2018 Vertex42 LLC
About This Template
Use this template within your project team to help clarify and communicate roles and responsibilities for each task or deliverable. Start by inserting rows to define the tasks and deliverables and insert columns as needed to define the roles of sponsors, leaders, consultants, and project team members. Customize the abbreviations below the chart based on the method you are using (RACI, DRASCI, CAIRO, etc.).
Terms of Use / Copyright
This template is a copyrighted work. Do not submit copies or modifications of this template to any website or online template gallery. Click on the link below to learn how you may or may not use this template.
License: Private Use Only
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.