## SA 1.1
|  | Project Name | COBER Insights | Date | 2019-11-17
|  | Project Number | 1001 | Document Number | SA 1.2
|  | Project Manager | Thomas Birmingham | Project Owner/Client | Matthew Krieger VP Technology
| Group Code | Stakeholder Name or Group Name. | IInternal Or External Stakeholder | Unaware, Resistant, Neutral, Supportive, or Leading? | Level of Influence (1-5, with 5 being the lowest) | Ability to Impact Resources (1-5) | Total Score | What does this stakeholder need? Stakeholder’s greatest concerns? | Communication Schedule | Strategy
Primary Stakeholders | A | Matthew Krieger | Internal | Supportive | 1 | 1 | 2 | Needs: better understanding of system security around data being stored in the cloud (risk & compliance), profit generated by DaaS Concerns: sufficent resources to complete project and then to training of resources for maintenance and selling DaaS | Bi-Weekly
|  | IT/Software Dev (Software Architect) | Internal | Leading, Supportive | 1 | 1 | 2 | Needs: software development, not limited to input from the various departments overseeing machine construction, sales to client and machine maintenance for how they interact and any possible constraints. Identifying of the right software and report parameters (requirement traceability). Concerns: limited understanding in non-expert user behaviors (ie. current/prospective clients). System security as it pertains to government projects. Building of COBER inhouse data collection device. | Weekly
| B | Electrical Mechanical Engineers | Internal | Resistant (pre-tech) / Supportive (post tech) | 4 | 3 | 7 | Needs: expertise input to help COBER being to build its own data collection device Concerns: understanding of how/if data impacts them | Quarterly
| C | Heating & Drying application technichians | Internal | Neutral | 3 | 2 | 5 | Needs: expertise input to help COBER being to build its own data collection device Concerns: understanding of how/if data impacts them | Quarterly
|  | Maintenance Technicians | Internal | Supportive | 2 | 2 | 4 | Needs: to be able to translate data analytics into value add for client and company. Turn data into a predictive maintenance feature for faster and more timely servicing of machines so that client does not loose machine hours Concerns: company may not provide sufficient training for field techs to assist clients | Monthly
| D | DBMA / CE | External | Leading, Supportive | 3 | 1 | 4 | Needs: understand how data is coded and storred from the data collection device Concerns: insufficient end user input on application reporting and views | Weekly
| E | Data Scientist | External | Leading | 3 | 2 | 5 | Needs: to know what data points are being captured by iDOL, how to analyze and report the data to make sense for end users, identifying value add data being captured Concerns: insufficient data collected | Weekly
Secondary Stakeholders | F | Flexy | External | Neutral | 2 | 2 | 4 | Needs: to ensure a quality product Concerns: COBER may try to strong arm relationship with supplier or look to build its own | Quarterly
| G | Existing Clients | External | Supportive; Neutral | 4 | 3 | 7 | Needs: to know what data points are being captured by iDOL, increase Concerns: report is not providing usefull enough information to help client reduce cost and increase productivity; application does not function properly; training in accessing and configuration to clients dashboard | Quarterly
Tertiary Stakeholder |  | Factory Floor Leaders | External | Unaware | 4 | 4 | 8 | Needs: to get the most productivity out of the machine Concerns: data collection device failure or incomplete data | Quarterly
|  | EC Machine Operators | External | Unaware | 4 | 4 | 8 | Needs: to get the most productivity out of the machine Concerns: data collection device failure or incomplete data | Quarterly
| H | New Clients | External | Unaware | 5 | 3 | 8 | Needs: how data is secured and how it could affect their bottom line Concerns: minimal | n/a
|  | NC Machine Operators | External | Unaware | 5 | 3 | 8 | Needs: how to undrestand the data to benefit their company Concerns: minimal | n/a
| I | Government | External | Resistant (pre-tech) / Supportive (post tech) | 5 | 5 | 10 | Needs: minimal Concerns: how securely data is stored and retrieved from the cloud | n/a

## links
https://cober.com/service-support/
System Service and Support Cober offers on-site support, calibrations, repairs and diagnostics and troubleshooting services. Remotely, Cober uses it’s Internet Diagnostics Online (iDOL) functionality to securely connect to your system over the Internet for diagnosis and remediation of operational issues. iDOL is installed as a standard part of all Cober oven products.
Preventative Maintenance We offer periodic preventative maintenance (PM) service programs on your equipment as well as training on PM processes and procedures.
Controls Programming Automation is key – we bring process automation to new and upgraded systems in the following areas: Process control Closed-loop power control for optimum heating Data collection and analysis